## 06bbfab2c62404018238775db58bb9e
Bug ID | Product | Component | Assignee | Status | Resolution | Summary | Changed | Defect Detection Phase | Opened | Priority | Reporter | Severity | SprintId | Task Id_Story id
25792 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | NEW | --- | Face detection is very slow. | 2021-10-25 11:42:37 | System Testing | 2021-10-25 11:42:37 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 10 | VM-85
25791 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | NEW | --- | Face detection through mobile. | 2021-10-25 11:41:38 | System Testing | 2021-10-25 11:41:38 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 10 | vm-84
25790 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | NEW | --- | Face detection through photographs. | 2021-10-25 11:45:08 | System Testing | 2021-10-25 11:40:30 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 10 | VM-85
25723 | \x{200b}VISAGE MVP2 | Employees | aswathy.shaji@naicoits.com | RESOLVED | FIXED | Exist time is recorded as entry time and vice-versa | 2021-10-14 15:39:57 | Acceptance Testing | 2021-10-14 15:24:14 | P2 - Critical | eldhose.paul@naicotech.com | Bug | VM sprint 10 | VM-106
25608 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | RESOLVED | FIXED | Time entered as NULL while user logout with user's credentials | 2021-10-14 16:36:44 | System Testing | 2021-09-24 17:14:27 | P2 - Critical | eldhose.paul@naicotech.com | Bug | VM SPRINT 8 | vm-108
25494 | \x{200b}VISAGE MVP2 | General | aneesh.pm@naicoits.com | NEW | --- | My time integration is not working | 2021-10-11 14:01:19 | System Testing | 2021-09-15 10:03:35 | P2 - Critical | eldhose.paul@naicotech.com | Bug | VM Sprint 8 | VM-106
25491 | \x{200b}VISAGE MVP2 | Devices | aneesh.pm@naicoits.com | NEW | --- | Face dataset functionality is not working | 2021-09-14 17:00:34 | System Testing | 2021-09-14 17:00:34 | P2 - Critical | eldhose.paul@naicotech.com | Bug | VM Sprint 8 | VM-73
25490 | \x{200b}VISAGE MVP2 | Devices | aswathy.shaji@naicoits.com | NEW | --- | Face liveness is not working | 2021-09-14 17:01:25 | System Testing | 2021-09-14 16:58:20 | P2 - Critical | eldhose.paul@naicotech.com | Bug | VM Sprint 8 | VM-85
25421 | \x{200b}VISAGE MVP2 | General | aneesh.pm@naicoits.com | NEW | --- | Fingerprint syn is not working properly | 2021-10-11 14:12:05 | System Testing | 2021-09-07 20:05:34 | P3 - High | eldhose.paul@naicotech.com | Bug | VM Sprint 7 | VM-42
25152 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | RESOLVED | FIXED | The user is able to enter the Server system after disabling the server toggle. | 2021-10-14 15:39:10 | System Testing | 2021-08-10 13:25:54 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 5 | APP-38
25149 | \x{200b}VISAGE MVP2 | General | aneesh.pm@naicoits.com | RESOLVED | WONTFIX | Fingerprint detected after its deletion for few seconds . | 2021-08-11 10:22:00 | System Testing | 2021-08-10 12:08:45 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 5 | APP-50
25148 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | REOPENED | --- | RFID and fingerprint data is not updated with employee’s name updation. | 2021-08-11 18:16:09 | System Testing | 2021-08-10 11:11:29 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 5 | APP-45
25147 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | REOPENED | --- | Unique RFID Code required pop-up is not coming while user scan with other employee RFID. | 2021-08-11 18:16:05 | System Testing | 2021-08-10 11:10:41 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 5 | VM 42
25083 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | CLOSED | FIXED | Process cancellation is not working after cancelling the fingerprint scan operation | 2021-08-17 16:26:12 | System Testing | 2021-08-03 16:56:28 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 4 | VM-52
25082 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | CLOSED | FIXED | The user is not able to enter the Server system after enabling the server toggle. | 2021-08-17 16:26:09 | System Testing | 2021-08-03 16:50:36 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 4 | VM-54
25080 | \x{200b}VISAGE MVP2 | General | aneesh.pm@naicoits.com | NEW | --- | The updated employee details is not reflected after update operation | 2021-08-03 16:57:35 | System Testing | 2021-08-03 12:41:32 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 4 | VM-45
25079 | \x{200b}VISAGE MVP2 | General | aneesh.pm@naicoits.com | NEW | --- | The updated employee details is not reflected after update operation | 2021-08-03 16:57:30 | System Testing | 2021-08-03 12:38:24 | P5 - Low | eldhose.paul@naicotech.com | Bug | Sprint 4 | VM-45
25078 | \x{200b}VISAGE MVP2 | Devices | aneesh.pm@naicoits.com | NEW | --- | The fingerprint is detected after Delete Fingerprint operation from mobile | 2021-08-03 12:39:40 | System Testing | 2021-08-03 12:19:00 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 4 | VM-50
25025 | \x{200b}VISAGE MVP2 | General | aneesh.pm@naicoits.com | NEW | --- | User can update RFID with other user’s RFID. | 2021-07-29 15:27:27 | System Testing | 2021-07-29 15:27:27 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 3 | VM-42
25024 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | CLOSED | FIXED | RFID updated for the user, but the mobile device shows RFID scan screen, then shows message as “RFID verification failed. Please try again“ | 2021-08-17 16:26:05 | System Testing | 2021-07-29 14:50:51 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 3 | VM-26
24980 | \x{200b}VISAGE MVP2 | General | aneesh.pm@naicoits.com | NEW | --- | The same user can add two RFID API while updating the RFID | 2021-07-23 13:27:32 | System Testing | 2021-07-23 13:27:32 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 3 | VM-42
24979 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | CLOSED | FIXED | Sometime RFID api call is not receiving in Device side. | 2021-08-17 16:26:01 | System Testing | 2021-07-23 13:15:44 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 3 | VM-26
24855 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | CLOSED | FIXED | Data Synchronization API is not working for first time | 2021-07-27 20:25:05 | System Testing | 2021-07-08 10:28:15 | P3 - High | eldhose.paul@naicotech.com | Bug | VM Sprint 2 | VM 32
24854 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | CLOSED | FIXED | Activate RFID API is not working first time | 2021-08-17 16:07:01 | System Testing | 2021-07-08 10:25:50 | P3 - High | eldhose.paul@naicotech.com | Bug | VM Sprint 2 | APP-24
24853 | \x{200b}VISAGE MVP2 | General | aswathy.shaji@naicoits.com | CLOSED | FIXED | Remote Door Access API is not working first. | 2021-07-27 20:25:01 | System Testing | 2021-07-08 10:23:57 | P3 - High | eldhose.paul@naicotech.com | Bug | VM Sprint 2 | VM-23
23736 | \x{200b}VISAGE MVP2 | Devices | nithin.varghese@naicoits.com | NEW | --- | Provide Proper option related to syn | 2021-03-19 15:48:10 | System Testing | 2021-03-19 15:48:10 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Sprint 12 | FDP-309
23735 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | NEW | --- | Application speak up incorrectly when user add name with uppercase | 2021-03-19 15:45:32 | System Testing | 2021-03-19 15:45:32 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 12 | FDP-291
23734 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | NEW | --- | Sync Employees Details is not working . | 2021-03-19 15:38:33 | System Testing | 2021-03-19 15:38:18 | P1 - Blocking | eldhose.paul@naicotech.com | Bug | Sprint 12 | FDP-289
23729 | \x{200b}VISAGE MVP2 | Devices | nithin.varghese@naicoits.com | NEW | --- | Delete Employee is not working | 2021-03-19 12:27:46 | System Testing | 2021-03-19 12:27:25 | P1 - Blocking | eldhose.paul@naicotech.com | Bug | Sprint 12 | FDP-317
23728 | \x{200b}VISAGE MVP2 | General | aji.g@naicoits.com | NEW | --- | Sometime face will detect ,but employee name is not speak up , if enter morethan one person in to office | 2021-03-19 15:45:45 | System Testing | 2021-03-19 12:25:42 | P3 - High | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-290
23441 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | RESOLVED | LATER | Application speak up incorrectly when user add name with uppercase | 2021-03-19 10:17:14 | Alpha Testing | 2021-02-24 17:10:47 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Sprint 12 | FDP-283
23439 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | RESOLVED | LATER | Login page :Clicking on Back link is navigate to Visage page | 2021-02-25 14:11:36 | System Testing | 2021-02-24 14:10:46 | P3 - High | eldhose.paul@naicotech.com | Bug | Alpha Testing | FDP-283
23420 | \x{200b}VISAGE MVP2 | General | aji.g@naicoits.com | RESOLVED | LATER | Sometime face will detect ,but employee name is not speak up , if enter morethan one person in to office | 2021-03-01 16:38:26 | Alpha Testing | 2021-02-23 14:16:21 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Alpha Testing | FDP-283
23407 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | RESOLVED | WONTFIX | Date and time format should be correct and same format for Entry and exit camera streaming. | 2021-02-25 14:13:14 | Alpha Testing | 2021-02-22 16:57:41 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Alpha Testing | FDP-283
23406 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | RESOLVED | WONTFIX | The message should be "Employees details already synchronized" while user try to synchronize Employee details that already synchronized. | 2021-02-25 14:15:58 | System Testing | 2021-02-22 16:52:00 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Alpha Testing | FDP-283
23405 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | RESOLVED | LATER | The message should be "Device already added" while user try to add a device that already added | 2021-02-25 14:17:48 | Alpha Testing | 2021-02-22 16:47:01 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Alpha Testing | FDP-283
23403 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | RESOLVED | LATER | Unauthorized Entry notification is receiving continually after face detection for valid user entry . | 2021-02-26 17:06:45 | Alpha Testing | 2021-02-22 11:42:57 | P3 - High | eldhose.paul@naicotech.com | Bug | Alpha Testing | FDP-283
23388 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | RESOLVED | LATER | Application should loading while adding server name as wrong | 2021-02-25 14:19:38 | Alpha Testing | 2021-02-19 15:41:46 | P3 - High | eldhose.paul@naicotech.com | Bug | Alpha Testing | FDP-283
23371 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | NEW | --- | Name says wrongly during Face detection after editing name | 2021-02-18 15:17:21 | Alpha Testing | 2021-02-18 15:15:41 | P3 - High | eldhose.paul@naicotech.com | Bug | FDP-283 | Alpha Testing
23286 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | User without server room access can enter to Server Room (Face Detection) | 2021-02-12 14:28:54 | Integration Testing | 2021-02-11 13:11:19 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23285 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | RESOLVED | LATER | User without server room access can enter to Server Room after updating access from employee details | 2021-03-19 10:47:02 | Integration Testing | 2021-02-11 13:08:33 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Sprint 12 | FDP-282
23245 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | Face detection is not working after Disable an Employee | 2021-02-25 14:21:45 | Integration Testing | 2021-02-10 16:25:19 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23243 | \x{200b}VISAGE MVP2 | Integration Testing | aji.g@naicoits.com | CLOSED | FIXED | Disable Employee option is not working | 2021-02-10 16:26:09 | Integration Testing | 2021-02-10 11:18:22 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23242 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | RESOLVED | LATER | Provide Proper option related to syn | 2021-03-19 15:47:21 | Integration Testing | 2021-02-10 11:17:14 | P3 - High | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23241 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | CLOSED | FIXED | Provide Proper messages related to syn | 2021-02-11 14:56:50 | Integration Testing | 2021-02-10 11:14:22 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23240 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | User is not able to add device through Bluetooth | 2021-02-12 14:29:00 | Integration Testing | 2021-02-10 09:53:50 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23231 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | RESOLVED | LATER | Close button is not working while a new user add his RFID for registration purpose | 2021-02-12 10:34:16 | Integration Testing | 2021-02-09 13:52:11 | P2 - Critical | eldhose.paul@naicotech.com | Enhancement | Integration Testing | FDP-282
23230 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | RESOLVED | LATER | Search field is not closed after after navigate from device list page to people listing page | 2021-02-12 10:39:09 | Integration Testing | 2021-02-09 12:48:37 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23229 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | User without server room access can enter to Server Room | 2021-02-11 13:03:01 | Integration Testing | 2021-02-09 11:19:48 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23214 | \x{200b}VISAGE MVP2 | Devices | nithin.varghese@naicoits.com | RESOLVED | LATER | The color of 'access to server' field should be blue after enable the field | 2021-02-12 10:38:36 | Integration Testing | 2021-02-08 16:10:22 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23207 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | RESOLVED | LATER | Unauthorized Entry notification is receiving for valid user entry | 2021-02-12 10:50:56 | Integration Testing | 2021-02-05 16:16:34 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23200 | \x{200b}VISAGE MVP2 | Integration Testing | aji.g@naicoits.com | RESOLVED | LATER | Face detection device identifies a person as another person | 2021-02-11 12:28:36 | Integration Testing | 2021-02-05 12:55:20 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
23199 | \x{200b}VISAGE MVP2 | Integration Testing | aji.g@naicoits.com | CLOSED | FIXED | Overlap of voice name while two person enters to the office | 2021-02-10 09:57:41 | Integration Testing | 2021-02-05 12:50:55 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22908 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | User is not able to delete the disabled employee | 2021-01-07 16:38:26 | Integration Testing | 2021-01-07 15:37:33 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22906 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | Person login with old name after changing the Name | 2021-01-07 14:49:55 | Integration Testing | 2021-01-06 17:32:29 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22905 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | Application allows smiley image for Device name | 2021-02-10 09:50:42 | --- | 2021-01-06 10:52:45 | P4 - Medium | eldhose.paul@naicotech.com | Task | Integration Testing | FDP-282
22904 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | Remove Employee option is not working properly | 2021-01-07 15:10:55 | Integration Testing | 2021-01-06 10:44:08 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22900 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | Provide character limit for search field | 2021-01-06 14:48:28 | Integration Testing | 2021-01-05 16:53:44 | P5 - Low | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22889 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | Emergency Exit notification is listed wrongly . | 2021-01-06 14:04:22 | --- | 2021-01-05 14:50:28 | P5 - Low | eldhose.paul@naicotech.com | Task | Integration Testing | FDP-282
22888 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | Add Fingerprint link should be disabled after adding 4 fingers | 2021-01-06 17:09:13 | Integration Testing | 2021-01-05 14:40:32 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22887 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | Entry & Exit Fingerprint Scanner is allowing access for Deleted Fingerprint | 2021-01-07 15:09:51 | Integration Testing | 2021-01-05 14:19:59 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22886 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | User is not able to add RFID for new user from mobile application | 2021-02-05 16:24:57 | Integration Testing | 2021-01-05 14:14:03 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22878 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | RESOLVED | WONTFIX | The main door is not open when the user clicks on the Remote Door Access button from mobile | 2021-02-05 12:13:49 | Integration Testing | 2021-01-05 12:20:13 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22877 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | Disable Employee option is delete the employee | 2021-01-07 14:48:01 | Integration Testing | 2021-01-05 12:09:36 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22875 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | Change Server is not working | 2021-01-06 14:01:26 | Integration Testing | 2021-01-05 11:06:56 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22874 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | Change Password is not working | 2021-01-05 17:02:18 | Integration Testing | 2021-01-05 10:52:34 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22873 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | Open Door button is not working while clicking on the top & most left-right side and it is not working in landscape mode | 2021-01-06 14:45:39 | Integration Testing | 2021-01-05 10:44:16 | P3 - High | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22872 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | Search text is not cleared when user click on back button | 2021-01-05 16:55:05 | Integration Testing | 2021-01-05 10:34:54 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22871 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | Sync Employees Details is not working . Showing a pop-up as 'Unexpected Error'. | 2021-02-11 13:32:25 | Integration Testing | 2021-01-05 10:31:32 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22870 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | RESOLVED | LATER | Labels for Entry and exit camera is not available | 2021-01-06 12:10:20 | Integration Testing | 2021-01-05 10:26:52 | P5 - Low | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22869 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | RESOLVED | WONTFIX | All old Notification pop-up daily for the first time use. | 2021-01-06 12:13:57 | Integration Testing | 2021-01-05 10:24:05 | P3 - High | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22864 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | Login is not works properly after logout from mobile application | 2021-01-05 17:10:04 | Integration Testing | 2021-01-04 15:26:45 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22861 | \x{200b}VISAGE MVP2 | Integration Testing | aji.g@naicoits.com | CLOSED | FIXED | AR (POD) Module: Push to talk Button Issues | 2021-02-11 15:45:52 | System Testing | 2021-01-04 14:22:55 | P3 - High | eldhose.paul@naicotech.com | Bug | Integration Testing | FDP-282
22776 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | RESOLVED | WONTFIX | Frames added incorrectly in DataSet | 2020-12-30 13:44:51 | System Testing | 2020-12-30 13:33:37 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-39
22775 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | An unwanted 'completed' text list after detected a bad video | 2021-01-05 17:01:14 | System Testing | 2020-12-30 13:03:17 | P4 - Medium | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-39
22755 | \x{200b}VISAGE MVP2 | Devices | aji.g@naicoits.com | RESOLVED | WONTFIX | Users cannot add device with correct wifi credentials while connecting to the application . | 2021-02-09 12:04:15 | System Testing | 2020-12-29 17:04:09 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-32
22754 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Device Bluetooth failed to connect with mobile Bluetooth | 2021-02-10 09:50:12 | System Testing | 2020-12-29 14:10:14 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-28
22741 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Cancel Button is not working on recording the face ID | 2020-12-30 13:24:26 | System Testing | 2020-12-28 14:50:56 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-39
22740 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | The video is not deleted after click ok on error msg | 2020-12-30 13:23:54 | System Testing | 2020-12-28 14:37:46 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-39
22738 | \x{200b}VISAGE MVP2 | Devices | nithin.varghese@naicoits.com | RESOLVED | WONTFIX | “Face detected“ message display when camera scans a blank surface. It can capture the blank surface | 2021-02-05 11:53:51 | System Testing | 2020-12-28 11:39:29 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-39
22710 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | FIXED | The notifications are not updating after clicking on the notification pop-up listed from mobile notification | 2020-12-30 13:19:51 | System Testing | 2020-12-23 16:21:35 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-260 FDP-75
22708 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | JSON Error occurred while adding the devices listed in mobile (add device page) without switch on the Bluetooth from FDP device | 2020-12-29 14:26:52 | System Testing | 2020-12-23 12:14:28 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-28
22707 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | User add device with wrong wifi credentials using Bluetooth . | 2020-12-29 17:04:24 | System Testing | 2020-12-23 12:05:40 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-32
22706 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | FIXED | The Bluetooth devices listing is not proper . Bluetooth devices listing after going through no result found page and shows improper loader | 2020-12-29 14:13:04 | System Testing | 2020-12-23 10:07:38 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-28
22703 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | The Video is captured is not saved in facedetection/facedetection_qa/face_detection/FDP/video | 2020-12-23 17:16:45 | System Testing | 2020-12-22 13:17:51 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-39
22700 | \x{200b}VISAGE MVP2 | Devices | aji.g@naicoits.com | CLOSED | FIXED | JSON Error occurred while connecting to Bluetooth of FDP device | 2020-12-29 14:12:50 | System Testing | 2020-12-21 16:14:25 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-31
22698 | \x{200b}VISAGE MVP2 | Devices | nithin.varghese@naicoits.com | CLOSED | FIXED | User is not able to connect the devices after disconnect the device. | 2020-12-29 14:12:43 | System Testing | 2020-12-21 14:53:48 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-28
22670 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | RESOLVED | FIXED | Fingerprint cancel pop-up is shown after adding a fingerprint | 2020-12-28 23:54:08 | System Testing | 2020-12-18 15:08:05 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-279
22669 | \x{200b}VISAGE MVP2 | Notifications | nanditha.vk@naicoits.com | CLOSED | FIXED | The notification redirection is not proper . Notification list after going through login page | 2020-12-23 16:14:55 | System Testing | 2020-12-18 13:50:16 | P3 - High | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-75
22668 | \x{200b}VISAGE MVP2 | Notifications | nanditha.vk@naicoits.com | CLOSED | FIXED | Application get closed after getting Emergency exit notification | 2020-12-22 17:08:56 | System Testing | 2020-12-18 12:50:45 | P2 - Critical | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-260
22666 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | CLOSED | FIXED | Application Entry and Exist functionality is not working with RFID and fingerprint . | 2020-12-21 17:10:34 | System Testing | 2020-12-18 11:10:30 | P1 - Blocking | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-281
22624 | \x{200b}VISAGE MVP2 | Notifications | monika.prakash@naicoits.com | CLOSED | FIXED | Notification is not listing in the application . | 2020-12-18 12:46:51 | System Testing | 2020-12-16 14:54:28 | P5 - Low | eldhose.paul@naicotech.com | Bug | Sprint 11 | FDP-75, FDP-260
22567 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | RESOLVED | FIXED | Its better to change voice response as 'Invalid access' instead of 'Invalid access,try again.'. | 2020-12-02 09:30:09 | --- | 2020-12-01 13:56:39 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 11 | FDP-18
22557 | \x{200b}VISAGE MVP2 | Devices | nithin.varghese@naicoits.com | RESOLVED | FIXED | Please validate the spacing in Configure Server page,Login page and Login pop up. | 2020-12-17 18:49:07 | --- | 2020-11-27 19:47:18 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 10 | NA
22520 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | RESOLVED | FIXED | Finger data is reading from the scanner even after finger activation is cancelled from mobile app | 2020-12-09 17:46:54 | System Testing | 2020-11-23 19:19:15 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-279
22519 | \x{200b}VISAGE MVP2 | Employees | nithin.varghese@naicoits.com | RESOLVED | LATER | Its better to provide password protection on launching the app after screen lock. | 2020-12-17 18:49:55 | --- | 2020-11-23 17:33:18 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 10 | FDP-72
22518 | \x{200b}VISAGE MVP2 | Employees | nithin.varghese@naicoits.com | RESOLVED | FIXED | Replace text as 'You will be logged out. Are you sure you still want to continue?'. | 2020-12-17 18:47:23 | --- | 2020-11-23 17:28:54 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 10 | FDP-84
22517 | \x{200b}VISAGE MVP2 | Employees | nithin.varghese@naicoits.com | RESOLVED | FIXED | Change the option name as 'Change Server' instead of 'Change Server Link'. | 2020-12-17 18:44:52 | --- | 2020-11-23 17:25:27 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 10 | FDP-84
22504 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | On clicking on back icon from full screen video,its displaying the full screen portrait mode video initially for seconds | 2020-11-23 18:43:46 | System Testing | 2020-11-19 21:47:41 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-82
22459 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Not getting any response for a long after calling api for edit employee face data. | 2020-11-17 22:14:04 | System Testing | 2020-11-17 16:06:35 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-98
22454 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Neither the video nor the images are getting saved even after the api shows the success message | 2020-11-17 20:13:46 | Acceptance Testing | 2020-11-16 20:06:59 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-98
22414 | \x{200b}VISAGE MVP2 | Employees | nanditha.vk@naicoits.com | CLOSED | FIXED | Displaying failure message on cancelling the add fingerprint operation. | 2020-12-01 11:37:48 | System Testing | 2020-11-12 21:09:33 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-279
22322 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | The face data set is not getting removed even after api gives the success message. | 2020-11-18 00:21:43 | System Testing | 2020-11-05 21:32:02 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-98
22299 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | CLOSED | WORKSFORME | The image is getting saved in the server in inverted position. | 2020-11-23 17:40:22 | System Testing | 2020-11-04 18:44:54 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-85
22291 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Getting 'Unexpected error' on calling unauthorized entry api using lager value as count | 2020-11-13 17:02:11 | System Testing | 2020-11-04 14:02:29 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-277
22290 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | In unauthorized entry table not only unauthorized but also authorized entries are getting saved.Either save only unauthorized entries or delete the authorized entries after a time stamp. | 2020-11-17 17:40:08 | System Testing | 2020-11-04 13:39:19 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-276
22289 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | In Unauthorized entry table ,there is no way to know the count of unauthorized entries happen.Its only saving the total count of entries. | 2020-11-13 17:12:36 | --- | 2020-11-04 13:36:39 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 10 | FDP-276
22255 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Displaying incorrect output message while passing employee id and cameraid that is not existing in face detection api. | 2020-11-12 23:26:03 | System Testing | 2020-11-02 18:03:23 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-270
22217 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Displaying incorrect message when user passes revoked employee id while calling face detection api | 2020-11-02 17:53:44 | System Testing | 2020-10-29 16:20:15 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 10 | FDP-270
22156 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | WORKSFORME | On provideing exit camera id,its not getting any voice response | 2020-10-29 11:03:28 | System Testing | 2020-10-26 00:17:04 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 9 | FDP-271
22107 | \x{200b}VISAGE MVP2 | Devices | nithin.varghese@naicoits.com | CLOSED | FIXED | Provide reason for the failure of fingerprint or RFID activation in mobile app,when user tries to activate fingerprints that are not matching or RFID which is already in use. | 2021-02-10 10:23:24 | --- | 2020-10-22 16:01:35 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 9 | FDP-40
22101 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | FIXED | On providing entry camera id,its getting voice response as Thank You Username | 2020-10-29 11:01:30 | System Testing | 2020-10-22 11:10:56 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 9 | TDL-271
22045 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | CLOSED | WONTFIX | Displaying only a static image with static date and time in camera streaming api.Its not even changing the time | 2020-10-22 12:27:16 | System Testing | 2020-10-16 20:42:30 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 9 | FDP-60
22028 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | FIXED | On calling api for voice transfer multiple times,should play the audio one after the other.Now its playing together | 2020-10-22 13:20:45 | System Testing | 2020-10-15 16:34:53 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 9 | FDP-71
21985 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | FIXED | In face detection api,upon giving exit camera id,the voice response provided is Welcome instead of 'Thank You <username>' | 2020-10-29 10:59:54 | System Testing | 2020-10-14 16:42:11 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 9 | FDP-271
21984 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | FIXED | On calling facedetection api ,voice response getting is only Welcome/Thank You and not appended the name | 2020-10-29 10:59:24 | Acceptance Testing | 2020-10-14 16:39:41 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 9 | FDP-271
21979 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Displaying 'Unexpected Error' on calling api for facedetection. | 2020-10-22 12:24:09 | Acceptance Testing | 2020-10-14 11:51:22 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 9 | FDP-270
21849 | \x{200b}VISAGE MVP2 | Employees | sandra.udayan@naicoits.com | CLOSED | FIXED | After running the api for voice transfer not getting the response in speaker | 2020-10-15 15:45:05 | System Testing | 2020-10-09 13:25:41 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 8 | FDP-88
21843 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | RESOLVED | FIXED | Not providing access for already registered fingerprint.Displaying message as invalid fingerprint when tried for access after activation. | 2020-11-12 13:20:04 | System Testing | 2020-10-08 18:24:44 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 8 | FDP-241
21829 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | WORKSFORME | Getting error message in device on calling api for voice command for outsider | 2020-10-15 16:23:59 | Acceptance Testing | 2020-10-07 19:35:36 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 8 | FDP-71
21778 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | CLOSED | FIXED | Displaying unexpected error on calling api requests and response for the chatbot | 2020-11-23 17:39:19 | System Testing | 2020-10-05 17:03:11 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 8 | FDP-87
21777 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Displaying message as Heart Beat fails (Error 400) ,even though device is active and device could find in DB. | 2020-11-23 17:39:02 | System Testing | 2020-10-05 16:38:34 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 8 | FDP-56
21776 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | RESOLVED | FIXED | Not able to train chatbot with new set of questions from NLU training section | 2020-10-08 09:51:18 | Acceptance Testing | 2020-10-05 16:14:21 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 8 | FDP-94
21775 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | RESOLVED | WONTFIX | Displaying incorrect response from chatbot for some questions | 2020-12-21 18:11:38 | System Testing | 2020-10-05 16:09:51 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 8 | FDP-94,FDP-87
21321 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | RESOLVED | FIXED | Displaying null value in bluetooth listing page. | 2020-12-11 09:16:59 | System Testing | 2020-09-18 17:47:03 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 7 | FDP-29
21318 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | CLOSED | WORKSFORME | Displaying incorrect message as 'Invalid Input Format' when a non existing employee code is provided as input | 2020-12-01 11:37:23 | System Testing | 2020-09-18 15:21:32 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 7 | FDP-83
21317 | \x{200b}VISAGE MVP2 | Devices | aji.g@naicoits.com | CLOSED | FIXED | Should disable the RFID/Fingerprint access on disabling the employee | 2020-10-06 17:11:28 | Acceptance Testing | 2020-09-18 14:52:24 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-19
21280 | \x{200b}VISAGE MVP2 | Employees | monika.prakash@naicoits.com | CLOSED | FIXED | Displaying 'Unexpected Error' after inserting attendance of an employee to employee table. | 2020-10-02 13:57:16 | Integration Testing | 2020-09-16 21:33:03 | P3 - High | swathy.cs@naicotech.com | Bug | Integration Testing | FDP-2
21278 | \x{200b}VISAGE MVP2 | Employees | nithin.varghese@naicoits.com | CLOSED | FIXED | No messages provided in mobile app if already access provided card is scanned for RFID activation for new employee | 2021-02-10 10:24:01 | System Testing | 2020-09-16 20:49:44 | P3 - High | swathy.cs@naicotech.com | Bug | Integration Testing | FDP-43
21141 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | RESOLVED | FIXED | Sometimes same device is displaying twice. | 2020-10-20 12:21:39 | System Testing | 2020-09-11 13:54:15 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
21140 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | The side menu is not disappearing while the permission pop up appears | 2020-09-16 21:56:58 | System Testing | 2020-09-11 13:48:47 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
21139 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | Displaying loader even when the permission pop up is displaying. | 2020-12-01 11:36:40 | System Testing | 2020-09-11 13:46:28 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
21126 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Getting unexpected error on providing input as json data. | 2020-10-22 12:25:50 | Acceptance Testing | 2020-09-10 16:50:34 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-88
21094 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | WORKSFORME | Displaying red indication on granting access when LED is connected to Arduino | 2020-10-07 16:53:28 | Acceptance Testing | 2020-09-09 21:15:29 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-261
21093 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | WORKSFORME | Displaying green indication on denying access when LED indicator is connected to arduino | 2020-10-07 16:34:08 | Acceptance Testing | 2020-09-09 21:14:05 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-261
21062 | \x{200b}VISAGE MVP2 | Employees | nanditha.vk@naicoits.com | CLOSED | FIXED | Replace text 'RF ID' into 'RFID' throughout the app. | 2020-09-11 15:03:16 | --- | 2020-09-09 14:36:37 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 6 | NA
21060 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | FIXED | LED is turning off in between after scanning RFID/fingerprint | 2020-10-22 15:37:58 | System Testing | 2020-09-09 14:13:05 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-261
21056 | \x{200b}VISAGE MVP2 | Employees | monika.prakash@naicoits.com | CLOSED | WORKSFORME | Displaying error message when user tries to change RFID data of an employee on clicking on Connect button | 2020-12-01 11:36:25 | System Testing | 2020-09-08 22:19:00 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-24
21055 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | FIXED | On scanning fingerprint on exit scanner ,LED indication in entry is blinking for both valid and invalid. | 2020-10-22 15:35:09 | Acceptance Testing | 2020-09-08 22:08:17 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-261
21052 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | FIXED | Voice response is not getting on scanning RFID card | 2020-10-22 15:36:35 | System Testing | 2020-09-08 21:02:17 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-261
21034 | \x{200b}VISAGE MVP2 | Notifications | nanditha.vk@naicoits.com | RESOLVED | LATER | No icons/count is displaying in notifications icon when app is open and user is in another page and received a push notification. | 2020-12-17 18:45:19 | Acceptance Testing | 2020-09-08 13:58:11 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-75
21033 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | On clicking on Ok,it should navigate back to the device listing page. | 2020-09-11 15:14:03 | System Testing | 2020-09-08 13:53:02 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
21032 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | Displaying success message even if the device is not available in the bluetooth range. | 2020-09-11 14:55:24 | System Testing | 2020-09-08 13:51:41 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
21031 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | Should list only the available devices on switching on the bluetooth.Now its displaying all the paired devices. | 2020-09-11 14:55:07 | Acceptance Testing | 2020-09-08 13:47:59 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
21030 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | Once the access is denied,should ask again for permission of bluetooth on clicking on Add Device option. | 2020-09-11 14:54:47 | System Testing | 2020-09-08 13:45:55 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
21029 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | The message 'No devices found.' should be aligned consistent as in the device listing page. | 2020-09-16 21:54:40 | Acceptance Testing | 2020-09-08 13:44:16 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
21028 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | FIXED | Pull to refresh is not working. | 2020-09-11 14:50:35 | System Testing | 2020-09-08 13:43:09 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-29
20991 | \x{200b}VISAGE MVP2 | Notifications | nanditha.vk@naicoits.com | RESOLVED | FIXED | On clicking on push notification,it should redirect directlt to notification page.Now its asking for permission pop up,then navigates to Add network screen before moving to notifications page.(Kill app and send push notification) | 2020-12-11 09:16:03 | System Testing | 2020-09-02 18:09:05 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-260,FDP-75
20990 | \x{200b}VISAGE MVP2 | Notifications | nanditha.vk@naicoits.com | RESOLVED | LATER | No icons/count is displaying in notifications icon when app is open and user is in another page and received a push notification. | 2020-12-17 18:45:40 | Acceptance Testing | 2020-09-02 18:06:43 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-260,FDP-75
20989 | \x{200b}VISAGE MVP2 | Notifications | nanditha.vk@naicoits.com | RESOLVED | FIXED | On calling emergency exit api multiple time,instead of increasing count of single push notification,its displaying multiple pushnotifications. | 2020-11-19 19:47:34 | Acceptance Testing | 2020-09-02 18:03:26 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 6 | FDP-260
20972 | \x{200b}VISAGE MVP2 | Integration Testing | kiran.mathew@naicoits.com | CLOSED | FIXED | Change all exit responses to Thank You instead of Welcome. | 2020-10-22 15:38:41 | --- | 2020-08-29 04:25:57 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 5 | FDP-18
20953 | \x{200b}VISAGE MVP2 | Integration Testing | nithin.varghese@naicoits.com | CLOSED | FIXED | The timeout response of fingerprint activation is getting delayed in mobile app. | 2020-10-22 15:54:10 | Integration Testing | 2020-08-28 22:40:02 | P3 - High | swathy.cs@naicotech.com | Bug | Integration Testing | FDP-40
20951 | \x{200b}VISAGE MVP2 | Integration Testing | aji.g@naicoits.com | CLOSED | FIXED | There is delay in triggering door access when a second employee tries for access using RFID card,after a first employee accessed the door. | 2020-11-23 17:38:11 | Integration Testing | 2020-08-28 22:32:55 | P3 - High | swathy.cs@naicotech.com | Enhancement | Integration Testing | FDP-223
20934 | \x{200b}VISAGE MVP2 | Employees | monika.prakash@naicoits.com | CLOSED | WORKSFORME | After revoking the access,getting success response in one scanner and no any response in other. | 2020-11-23 17:38:06 | Integration Testing | 2020-08-28 15:38:27 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-68
20933 | \x{200b}VISAGE MVP2 | Employees | nithin.varghese@naicoits.com | CLOSED | FIXED | Fingerprint Activation:Even after displaying fingerprint not matching message in the device,not displaying any message in the mobile app. | 2020-10-22 15:52:22 | Integration Testing | 2020-08-28 15:20:37 | P3 - High | swathy.cs@naicotech.com | Bug | Integration Testing | FDP-40
20930 | \x{200b}VISAGE MVP2 | General | kiran.mathew@naicoits.com | CLOSED | FIXED | Reduce the delay in voice responce of RFID successful access | 2020-12-01 11:33:41 | --- | 2020-08-28 14:20:54 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 5 | FDP-18
20929 | \x{200b}VISAGE MVP2 | General | kiran.mathew@naicoits.com | CLOSED | FIXED | Should provide the name of the employee in the message of Fingerprint access like in RFID. | 2020-08-28 21:48:06 | System Testing | 2020-08-28 14:15:30 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-18
20927 | \x{200b}VISAGE MVP2 | Notifications | sandra.udayan@naicoits.com | CLOSED | FIXED | Not listing the emergency exit notification upon calling the notifications api. | 2020-08-28 22:12:52 | Acceptance Testing | 2020-08-28 13:29:28 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-258
20912 | \x{200b}VISAGE MVP2 | Devices | nanditha.vk@naicoits.com | CLOSED | WORKSFORME | Application got crashed on multiple attempts done for disabling employee. | 2020-09-18 13:33:54 | System Testing | 2020-08-27 16:50:54 | P1 - Blocking | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-257
20908 | \x{200b}VISAGE MVP2 | Devices | sandra.udayan@naicoits.com | CLOSED | FIXED | Displaying message as 'Device not found' on calling emergency exit api'. | 2020-08-28 11:59:19 | Acceptance Testing | 2020-08-27 15:17:25 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-258
20907 | \x{200b}VISAGE MVP2 | Employees | nanditha.vk@naicoits.com | CLOSED | WORKSFORME | Should disable the RFID/Fingerprint access on disabling the employee | 2020-09-18 14:05:04 | Acceptance Testing | 2020-08-27 14:30:16 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 5 | TDL-257
20906 | \x{200b}VISAGE MVP2 | Employees | nanditha.vk@naicoits.com | CLOSED | FIXED | Replace text as 'Are you sure you want to enable access?' while trying to enable the disabled user. | 2020-09-11 14:57:10 | --- | 2020-08-27 14:21:18 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 5 | FDP-257
20905 | \x{200b}VISAGE MVP2 | Employees | nanditha.vk@naicoits.com | CLOSED | WORKSFORME | Should allow to enable employee once access is revoked. | 2020-09-16 21:03:46 | Acceptance Testing | 2020-08-27 14:16:18 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-257
20904 | \x{200b}VISAGE MVP2 | Employees | nanditha.vk@naicoits.com | CLOSED | WORKSFORME | On clicking on Enable Employee option,its displaying wrong validation message as 'Already access revoked.'. | 2020-09-16 21:03:25 | System Testing | 2020-08-27 14:10:23 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-257
20841 | \x{200b}VISAGE MVP2 | Devices | monika.prakash@naicoits.com | CLOSED | FIXED | Should not allow to use the same camera by multiple devices. | 2020-08-27 22:31:54 | System Testing | 2020-08-25 17:16:32 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-54
20837 | \x{200b}VISAGE MVP2 | Notifications | sandra.udayan@naicoits.com | CLOSED | FIXED | Displaying unexpected error on calling api for notification listing. | 2020-08-28 12:04:43 | Acceptance Testing | 2020-08-25 16:35:48 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-258
20833 | \x{200b}VISAGE MVP2 | Notifications | sandra.udayan@naicoits.com | CLOSED | FIXED | Displaying some default time when user enters only date as accesstime | 2020-08-28 12:02:54 | System Testing | 2020-08-25 16:24:47 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-258
20832 | \x{200b}VISAGE MVP2 | Notifications | sandra.udayan@naicoits.com | CLOSED | FIXED | Dislaying unexpected error on providing invalid access time. | 2020-08-28 12:02:33 | System Testing | 2020-08-25 16:22:49 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 5 | FDP-258
20784 | \x{200b}VISAGE MVP2 | Notifications | nanditha.vk@naicoits.com | CLOSED | FIXED | There is no sound, vibration or led indication when the push notification is received | 2020-09-11 11:42:59 | Acceptance Testing | 2020-08-24 15:22:02 | P4 - Medium | meenu.joy@naicoits.com | Bug | Sprint 5 | FDP-75
20774 | \x{200b}VISAGE MVP2 | Notifications | nanditha.vk@naicoits.com | CLOSED | FIXED | Getting Unexpected error for unauthorized entry api | 2020-09-07 12:16:45 | Acceptance Testing | 2020-08-24 12:32:59 | P3 - High | meenu.joy@naicoits.com | Bug | Sprint 5 | FDP-75
20773 | \x{200b}VISAGE MVP2 | Devices | kiran.mathew@naicoits.com | CLOSED | FIXED | LED indicator is turned off after scanning RFID | 2020-08-28 14:10:43 | Acceptance Testing | 2020-08-24 11:21:59 | P2 - Critical | meenu.joy@naicoits.com | Bug | Sprint 5 | FDP-5
20745 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | Delay in displaying failure message in the mobile app if RFID card is not scanned even after timeout. | 2020-11-23 13:33:46 | Integration Testing | 2020-08-21 21:06:01 | P3 - High | swathy.cs@naicotech.com | Bug | Integration Testing | FDP-43
20744 | \x{200b}VISAGE MVP2 | Integration Testing | monika.prakash@naicoits.com | CLOSED | FIXED | While trying to access door using already registered RFID card,its displaying validation message as INVALID CARD. | 2020-09-11 11:42:49 | Integration Testing | 2020-08-21 21:03:38 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 4 | FDP-24
20735 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | RESOLVED | FIXED | Sort the available devices | 2020-12-21 16:36:44 | --- | 2020-08-21 19:28:59 | P3 - High | meenu.joy@naicoits.com | Enhancement | Sprint 5 | FDP-75
20717 | \x{200b}VISAGE MVP2 | Employees | sandra.udayan@naicoits.com | CLOSED | FIXED | Device access are not updating while editing the Employee details | 2020-08-21 10:57:07 | Acceptance Testing | 2020-08-20 16:39:09 | P3 - High | meenu.joy@naicoits.com | Bug | Sprint 5 | FDP-256
20583 | \x{200b}VISAGE MVP2 | Notifications | sandra.udayan@naicoits.com | CLOSED | FIXED | Should display "No notifications found" if there is no data to display | 2020-08-14 20:59:42 | Acceptance Testing | 2020-08-14 15:53:41 | P3 - High | meenu.joy@naicoits.com | Bug | FDP Sprint 4 | FDP-254
20582 | \x{200b}VISAGE MVP2 | Notifications | sandra.udayan@naicoits.com | CLOSED | FIXED | Wrong time is displayed in Notifications list API | 2020-08-19 12:06:13 | Acceptance Testing | 2020-08-14 15:26:53 | P3 - High | meenu.joy@naicoits.com | Bug | FDP Sprint 4 | FDP-254
20553 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Give header "Setup Fingerprint" and cancel button | 2020-12-01 11:33:28 | --- | 2020-08-13 19:30:52 | P3 - High | meenu.joy@naicoits.com | Enhancement | FDP Sprint 4 | FDP-38
20516 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | Alert message change in API | 2020-09-11 11:42:53 | --- | 2020-08-12 15:32:10 | P3 - High | meenu.joy@naicoits.com | Enhancement | FDP Sprint 4 | FDP-38
20515 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | FIXED | Enhancement on mobile 'Alert' popup | 2020-08-24 11:36:51 | --- | 2020-08-12 12:55:56 | P3 - High | meenu.joy@naicoits.com | Enhancement | FDP-Sprint 4 | FDP-38
20485 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | FIXED | Time for the unauthorized entry is not updating | 2020-08-11 16:10:28 | Acceptance Testing | 2020-08-11 10:17:58 | P3 - High | meenu.joy@naicoits.com | Bug | FDP Sprint 4 | FDP-251
20414 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | CLOSED | FIXED | Space before and after the Device Unique ID is not trimmed | 2020-08-06 14:13:31 | System Testing | 2020-08-05 18:29:03 | P4 - Medium | meenu.joy@naicoits.com | Bug | FDP Sprint 4 | FDP-246
20413 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | CLOSED | FIXED | Device unique ID for Logout API is not mandatory | 2020-08-06 14:15:16 | System Testing | 2020-08-05 18:21:38 | P4 - Medium | meenu.joy@naicoits.com | Bug | FDP Sprint 4 | FDP-246
20350 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Ask for confirmation of discard changes when user tries to navigate back without saving changes from the Edit Employee page. | 2020-08-12 15:31:01 | --- | 2020-07-31 18:41:56 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 3 | FDP-38
20349 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Some times displaying double loaders at top and centre while moving back to emplyee listing page from details page. | 2020-08-06 13:32:36 | System Testing | 2020-07-31 18:36:55 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-38
20344 | \x{200b}VISAGE MVP2 | General | aji.g@naicoits.com | CLOSED | FIXED | Fingerprint which is added upon editing the employee is not listing in Fingerprints page. | 2020-08-04 13:04:22 | System Testing | 2020-07-31 16:08:22 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-38
20340 | \x{200b}VISAGE MVP2 | General | aji.g@naicoits.com | CLOSED | FIXED | Getting error upon trying to add multiple fingerprint for same employee. | 2020-07-31 17:04:58 | System Testing | 2020-07-31 11:18:06 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-52
20322 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | WONTFIX | Getting 'Unexpected error' on trying to sync the device. | 2020-09-11 11:42:30 | System Testing | 2020-07-30 15:06:03 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-240
20321 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | Replace success message as 'The employee is removed successfully.' once Remove employee is successful. | 2020-08-03 10:06:05 | --- | 2020-07-30 14:39:28 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 3 | FDP-42
20320 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | FIXED | Replace the text as 'Synced successfully.' once the sync process is successful. | 2020-08-07 13:12:10 | System Testing | 2020-07-30 14:32:05 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-240
20319 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | Listing the names of removed employees on Searching. | 2020-08-01 23:40:31 | System Testing | 2020-07-30 13:52:18 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-242
20302 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | RESOLVED | WONTFIX | Displaying alert of incorrect password even after entering the correct password. | 2020-12-15 09:46:38 | System Testing | 2020-07-30 10:07:35 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-92
20274 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | User is asked to save already saved employee id and employee code when trying to edit only RFID/Fingerprint. | 2020-08-01 23:21:05 | System Testing | 2020-07-29 12:32:19 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-38
20261 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | CLOSED | FIXED | Should display failure message instead of exception if API call fails. | 2020-07-29 13:56:19 | System Testing | 2020-07-28 14:04:45 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-16
20260 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | Should trim the leading and trailing spaces while search | 2020-07-29 14:16:54 | System Testing | 2020-07-28 13:41:53 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-242
20258 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | User is not able to add a device once removed. | 2020-08-01 23:20:38 | System Testing | 2020-07-28 13:17:59 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-76
20257 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Displaying only a loading symbol while clicking on Open in Device details page. | 2020-08-01 23:17:18 | System Testing | 2020-07-28 12:45:18 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-81
20256 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Replace text as 'Deleted successfully.' upon removing a device | 2020-08-01 23:16:51 | System Testing | 2020-07-28 12:41:55 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 3 | FDP-27
20175 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | CLOSED | FIXED | Getting exception while trying to call API using an empty device id. | 2020-07-24 20:27:28 | System Testing | 2020-07-24 14:40:10 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 3 | FDP-16
20091 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | CLOSED | FIXED | Displaying exception on calling the API for remote door access. | 2020-07-18 21:24:28 | System Testing | 2020-07-18 20:52:25 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-67
20089 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Listing of fingerprints should be in sorted order. | 2020-08-01 23:16:27 | --- | 2020-07-18 01:12:46 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-37
20074 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | FIXED | The padding from the left end seems different .Please verify. | 2020-07-18 00:57:47 | System Testing | 2020-07-17 13:25:55 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-76
20073 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | FIXED | Please verify the font given in the notifications page | 2020-07-18 00:57:22 | System Testing | 2020-07-17 13:24:21 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-76
20071 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | WONTFIX | The duration(like 1d) is given after the device in the UI design which is missing in application in Notifications page. | 2020-07-18 00:56:58 | System Testing | 2020-07-17 13:22:48 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-76
20070 | \x{200b}VISAGE MVP2 | General | nanditha.vk@naicoits.com | CLOSED | FIXED | The header should be as 'Notifications' instead of 'Notification'. | 2020-07-18 00:55:26 | System Testing | 2020-07-17 13:21:21 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-76
20044 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | If the menus given at the right of Add RFID,Add Fingerprint and Add FaceID in employee page has no any functionality ,replace it with a arrow head for navigating to next page. | 2020-07-18 00:45:54 | --- | 2020-07-16 20:42:46 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-37
20043 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | If the menus given at the right of Add RFID,Add Fingerprint and Add FaceID in employee page has no any functionality ,replace it with a arrow head for navigating to next page. | 2020-07-18 00:45:37 | --- | 2020-07-16 20:42:33 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-37
20042 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Should ask the user the confirmation for deleting the existing RF ID for adding new one instead of directly going to Add RF ID page. | 2020-07-18 00:45:00 | --- | 2020-07-16 20:39:55 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-37
20039 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | The pop up for Add Fingerprint should be same as in the design | 2020-07-18 00:44:24 | System Testing | 2020-07-16 17:23:26 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-37
20038 | \x{200b}VISAGE MVP2 | General | sandra.udayan@naicoits.com | CLOSED | FIXED | On revoking the access of employee,the message displayed as 'Deleted Successfully'. | 2020-07-18 00:44:05 | System Testing | 2020-07-16 15:56:46 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-68
20028 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Replace alert as 'Fingerprint verification failed.Please try again.'. | 2020-07-18 00:43:40 | System Testing | 2020-07-16 13:58:24 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-40
20024 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Replace alert message for delete finger print as 'Are you sure you want to delete the fingerprint?' | 2020-07-18 00:43:00 | --- | 2020-07-16 12:13:51 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-37
20022 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Replace 'x' icon with back arrow icon for navigating to listing page,after saving name and ID. | 2020-07-18 00:42:38 | --- | 2020-07-16 11:49:36 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-37
20021 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Disable the Add Fingerprint option when the limit exceeds. | 2020-07-18 00:42:22 | System Testing | 2020-07-16 11:47:37 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-37
20018 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | The footer seems on the top of soft keyboard on clicking on the textfields in Login screen | 2020-07-18 00:41:20 | System Testing | 2020-07-16 10:24:21 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-72
19997 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | On clicking on connect for scan RFID, it shows the animated view for a second and then disappears and again shows the screen for connect. | 2020-07-16 11:54:11 | System Testing | 2020-07-15 11:39:28 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-24
19996 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | On clicking on connect for scan Fingerprint,click on connect it navigates back to fingerprint page. | 2020-07-16 16:45:27 | System Testing | 2020-07-15 11:37:59 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-34
19992 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Replace mandatory field validation message as 'Please enter Full name.' in the name Full name field and 'Please enter Employee ID.' in the Employee ID field | 2020-07-16 16:45:08 | System Testing | 2020-07-14 21:45:24 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-37
19991 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Replace text as 'We have successfully saved employee details.' while saving the employee id and name in Add Employee page. | 2020-07-16 16:43:17 | System Testing | 2020-07-14 20:20:21 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 2 | FDP-37
19986 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | LATER | After saving Employee id and name,couldnt find the employee details in the employee listing page. | 2020-07-16 16:42:29 | --- | 2020-07-14 10:22:27 | P3 - High | swathy.cs@naicotech.com | Task | Sprint 2 | FDP-37
19985 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | DUPLICATE | The toggle bar is not able to enable once id and name is saved | 2020-07-16 16:42:02 | System Testing | 2020-07-14 10:21:18 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-37
19984 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | INVALID | The toggle bar is nt able to enable once id and name is saved | 2020-07-16 16:41:42 | System Testing | 2020-07-14 10:19:42 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-37
19983 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | The name of toggle bar is Access to Server System | 2020-07-16 16:41:16 | System Testing | 2020-07-14 10:14:26 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-37
19982 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Accepting even digits as Employee name. | 2020-07-16 16:40:31 | System Testing | 2020-07-14 10:12:22 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-37
19979 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | The Security is not getting updating in DB after calling edit API. | 2020-07-14 11:15:13 | System Testing | 2020-07-13 19:22:43 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 2 | FDP-10
19835 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | The data is updating only in Dev DB. | 2020-07-16 16:38:14 | System Testing | 2020-07-03 17:45:41 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-26
19820 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Display success message even if wrong password is given. | 2020-07-28 14:17:34 | System Testing | 2020-07-03 15:39:08 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92
19819 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Replace the text as 'Are you sure you want to Logout?' instead of 'Are you sure you want to logout?' . | 2020-07-03 20:41:48 | System Testing | 2020-07-03 14:02:39 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-74
19818 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Search using period only displaying incorrect result. | 2020-07-03 20:41:16 | System Testing | 2020-07-03 13:40:27 | P5 - Low | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-91
19817 | \x{200b}VISAGE MVP2 | General | christy.sunny@naicoits.com | CLOSED | FIXED | Displaying exception if employee code field is kept blank. | 2020-07-03 17:06:13 | System Testing | 2020-07-03 11:42:40 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-26
19804 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Provide period(.) at the end of all validation messages. | 2020-07-03 15:35:18 | --- | 2020-07-01 21:05:10 | P4 - Medium | swathy.cs@naicotech.com | Enhancement | Sprint 1 | FDP-92
19803 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Remove the numerics given before the header 'Choose a network to continue'. | 2020-07-03 12:51:06 | System Testing | 2020-07-01 20:45:48 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92,FDP-96
19802 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | RESOLVED | WONTFIX | After the time out provided in permission pop up,the app is automatically enabling Wifi and listing the available Wifi. | 2020-12-15 09:45:54 | System Testing | 2020-07-01 20:37:08 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92
19801 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Replace text as No network available instead of No data available if there are no networks available for pairing | 2020-07-03 14:19:59 | System Testing | 2020-07-01 20:35:00 | P4 - Medium | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92
19800 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | RESOLVED | WONTFIX | Not listing available WiFi after enabling WifI option. | 2020-12-15 09:47:05 | System Testing | 2020-07-01 20:33:00 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92
19799 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Even without connecting to a network,displayed as Connected in the Welcome screen | 2020-07-03 20:40:41 | System Testing | 2020-07-01 20:30:11 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92
19798 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Even without enabling toggle button Wifi listing can be viewed. | 2020-07-03 15:23:12 | System Testing | 2020-07-01 20:20:27 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92
19797 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | Pages should be responsive in landscape mode. | 2020-07-03 12:47:21 | System Testing | 2020-07-01 20:16:22 | P3 - High | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92
19796 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | The icon displayed while entering password seems confusing. | 2020-07-03 12:42:22 | System Testing | 2020-07-01 17:52:40 | P3 - High | swathy.cs@naicotech.com | Enhancement | Sprint 1 | FDP-92
19794 | \x{200b}VISAGE MVP2 | General | nithin.varghese@naicoits.com | CLOSED | FIXED | User is able to get connected to Wifi even without any giving password. | 2020-07-03 17:12:46 | System Testing | 2020-07-01 17:37:17 | P2 - Critical | swathy.cs@naicotech.com | Bug | Sprint 1 | FDP-92
19792 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | Attendance status is always displayed as false | 2020-07-02 16:17:05 | Acceptance Testing | 2020-07-01 16:03:16 | P4 - Medium | meenu.joy@naicoits.com | Bug | FDP Sprint 1 | FDP-2
19695 | \x{200b}VISAGE MVP2 | General | monika.prakash@naicoits.com | CLOSED | FIXED | Getting Exception when not giving the Device code | 2020-07-03 16:06:42 | Acceptance Testing | 2020-06-26 17:22:08 | P4 - Medium | meenu.joy@naicoits.com | Bug | FDP Sprint 1 | FDP-48